Szempont

Execution Specification — Min & Max Builds

In-store sales & order platform replacing ClearVis.io at ClearVis store, Teréz körút 50

Version 2 · 12 July 2026 · eOptika AI

# Contents

# 1. Overview & Objectives

Build an in-house, in-store sales and order-capture platform ("Szempont") to replace ClearVis.io as the point-of-sale layer at the Teréz körút 50 store, reusing the existing eOptika GCP/BigQuery/Cloud Run stack, the Unas order pipeline, the IRIS identity spine, and the Atlas admin UI design system.

Two build scenarios are specified. MIN is the "sales floor order engine": lens catalog ingest, quoting, customer lookup, and order capture routed through the proven Unas → Tharanis flow. MAX extends MIN into a full ClearVis replacement (excluding exam/appointment booking, which becomes its own engine) via thin integration contracts to IRIS (Rx), Műhely software (glazing), Szamlazz.hu (NAV invoicing), and the GC eOptika communications module (notifications), plus in-store inventory, ClearVis data migration, and multi-store readiness.

## 1.1 Explicitly out of scope

- Exam / appointment booking — separate engine, separate project and chat.

- Rx / EHR module build — lives in IRIS; Szempont only consumes/writes via a contract (M6).

- Műhely workflow engine — its own software project; Szempont only hands off orders and receives status (M7).

- Certified fiscal hardware (pénztárgép) replacement — existing certified device stays standalone; invoicing is via Szamlazz.hu API (M8). CONFIRMED (v2): invoice-per-sale via Szamlazz.hu satisfies nyugta/pénztárgép rules for Teréz50 cash sales — no fiscal hardware dependency remains.

- Payment terminal software integration — payment method is recorded, not processed, in both builds (candidate future module).

## 1.2 Scenario summary

| Scenario | Engineer-days | Sabie-days | Calendar |
| --- | --- | --- | --- |
| MIN (M1–M5) | 14–18 | 4.5–6.5 | 3–4 weeks (dedicated review slot) |
| MAX (M1–M12) | 35–50 | 12–16 | 6–9 weeks incl. parallel-run |

Token cost: MIN ~$500–900; MAX ~$1,500–2,500. External cash costs near zero (Szamlazz.hu already in use; no fiscal hardware project).

# 2. Architecture Principles & Reuse Map

- GCP project natural-caster-496309-j3, region europe-west1. New BigQuery dataset: szempont. House rule: every BigQuery job labelled tool=szempont.

- Repo: eoptikaltd/szempont (private). Claude Code project folder: ~/Desktop/Claude folder/szempont, generic ~/.claude/CLAUDE.md house rules apply.

- Frontend on the Atlas dev kit: design system v1.1, page archetypes, central nav.json on assets.atlas.eoptika.hu, 3-tier density system. Brand: cream #FBF7EE / gold #C9A961 / ink #1A1A1A, Cormorant Garamond + DM Sans.

- Host (decided v2): szempont.eoptika.hu, IAP-protected; Atlas design system regardless of host.

- Catalog split (decided v2): the full lens variant catalog (~500K SKUs) lives in BigQuery only; ERP/Unas hold sold SKUs only, provisioned on first sale (M4 SKU promotion). Szempont is the manager of this lens database — same division of labour as the current ClearVis setup.

- Order write path (decided): create orders in Unas via API flagged as store-channel; existing Unas → Tharanis flow carries ERP posting. No direct Tharanis SOAP writes in either build.

- Identity: consume IRIS A-grade fulfilment zone only; never mint own person IDs; Z1 fallback contract for unresolved walk-ins.

- Product master: Unas products (already in unas_data) + warehouse enrichment tables; images via Unas CDN URLs.

- All external integrations (IRIS Rx, Műhely, GC comms) are built against stub contracts so Szempont never blocks on sibling projects.

# 3. MIN Build — Sales Floor Order Engine (M1–M5)

Goal: staff can quote and capture spectacle and contact-lens orders on the floor, against live supplier lens catalogs and the real customer identity, with a printable munkalap — in one tool. Everything downstream (ERP posting, invoicing, fulfilment) rides existing pipelines.

### M1 — Lens Catalog Ingest (FS6/SF6) — via existing FS6 Converter

Priority: P0

Estimate: 2–3 engineer-days · 0.5 (validation) Sabie-days

Purpose: Ingest supplier spectacle-lens price lists (SF6/FS6 standard, 11-file ZIP) into BigQuery as the pricing source of truth. RESOLVED (v2): all branded manufacturers — Zeiss, Hoya, Essilor, Noptiker — publish FS6; Luxottica original lenses (Ray-Ban/Oakley, not currently sold) would arrive in a custom format; eOptika private-label lenses can be published in FS6. The existing eOptika "FS6 Converter" (FS6-to-eOptika-and-back, on GitHub) is reused as the parser — this module is integration, versioning and overrides, not parser development.

Functionality (user-facing):

- Upload or scheduled pull of supplier catalog ZIPs, parsed through the FS6 Converter into the szempont BigQuery schema.

- Full catalog lives in BigQuery only (~500K possible SKUs); the ERP/Unas receive nothing at ingest time — see M4 SKU promotion. This mirrors the current ClearVis setup and avoids SKU overload (<5% of variants ever sell).

- Versioned catalogs with valid-from/until; old versions retained for quote reproducibility.

- Override table for negotiated combination prices not representable in SF6 (pattern: ext_cogs_corrections).

- Catalog health report: row counts, price deltas vs previous version, missing-surcharge warnings.

Build tasks (technical):

- Wrap FS6 Converter as a Cloud Run job szempont-catalog-ingest; land into schema szempont.lens_catalog_* (head, types, geometries, prices, coatings, colors, surcharges) with catalog_version keys.

- Override table szempont.lens_price_overrides with effective-dating.

- Idempotent re-ingest; unit tests reuse Converter test fixtures; Cloud Scheduler optional.

Interfaces:

- Input: supplier ZIP (GCS drop bucket) → FS6 Converter. Output: BigQuery szempont.* tables consumed by M2/M4.

Dependencies: FS6 Converter repo (exists, GitHub).

Acceptance: One full supplier catalog (e.g. Hoya) ingested via the Converter, spot-checked against printed price list; override applied correctly in a test quote.

### M2 — Pricing Engine + Lens Picker / Quote Builder

Priority: P0

Estimate: 4–5 engineer-days · 1.5 (pricing rules + UX review) Sabie-days

Purpose: The core floor tool: parametric lens search, side-by-side comparison, and quote generation with correct base + surcharge + option pricing and margin visibility.

Functionality (user-facing):

- Parameter-first search: Rx range, index, design (SV/progressive/office), coating tier, photochromic, diameter → matching lenses across suppliers.

- Compare 2–3 candidate lenses side by side with retail price, cost, margin; margin-sorted "best glass" default.

- Quote = frame line (from Unas product search incl. image) + lens lines + options; house rounding rules; discount entry with permission gating.

- Quote save / retrieve / print (branded PDF); quote converts to order in one step (M4).

Build tasks (technical):

- Pricing engine as a pure library with test suite (base price + surcharges + combo overrides + VAT).

- Atlas archetype pages: search/compare view, quote editor; product search against unas_data + enrichment tables, images via Unas CDN.

- Quote persistence in szempont.quotes with full price-component breakdown for audit.

Interfaces:

- Reads szempont.lens_catalog_*, unas_data products. Writes szempont.quotes.

Dependencies: M1.

Acceptance: Staff can produce a correct 3-option comparison and branded quote PDF for a real Rx in under 3 minutes; prices match manual calculation on 20 test cases.

### M3 — Customer Layer (IRIS lookup / create)

Priority: P0

Estimate: 2 engineer-days · 0.5 Sabie-days

Purpose: In-store customer = the same person as the web customer. Look up, disambiguate, or create identities against the IRIS spine; show cross-channel context on the floor.

Functionality (user-facing):

- Search by name / phone / email / order number; disambiguation cards with recent purchases and store/web channel history.

- Create new walk-in customer with minimal fields; GDPR consent capture (marketing opt-in flag passed onward).

- Household hints surfaced read-only (family pickup scenarios).

Build tasks (technical):

- Read from IRIS A-grade fulfilment zone; Z1 fallback contract for unresolved identities; never mint person IDs locally.

- Thin service layer + Atlas lookup component reused across M2/M4 screens.

Interfaces:

- IRIS read contract (existing); Z1 fallback (existing, per WIMO).

Dependencies: IRIS identity spine (live).

Acceptance: Lookup returns the correct person for 20 known test customers incl. accent/diacritic variants; new walk-in flows into IRIS via agreed path without duplicate creation.

### M4 — Order Capture → Unas + Munkalap PDF + SKU Promotion

Priority: P0

Estimate: 5–6 engineer-days · 1.5 (flow review + floor UAT) Sabie-days

Purpose: Convert quotes (or direct entries) into real orders in the Unas store-channel, and produce the workshop worksheet (munkalap) that today drives glazing. RESOLVED (v2): no generic/custom SKUs from now on — every lens variation carries its own SKU. The full variant catalog lives only in BigQuery (M1); this module promotes a SKU into ERP/Unas the first time it is actually sold.

Functionality (user-facing):

- Spectacle order: frame + lens pair + Rx values + fitting measurements (PD, heights) + options; CL and accessory orders: standard product lines.

- SKU promotion: if the quoted lens variant does not yet exist in Unas/Tharanis, it is auto-created (from its BigQuery catalog record) before the order is written — invisible to staff, logged for audit.

- Payment method and deposit/partial amount recorded (not processed); balance shown at pickup.

- Order confirmation printed / emailed; munkalap PDF generated with all glazing-relevant data; order status visible (from Unas status pull).

- Edit/cancel window rules before ERP posting.

Build tasks (technical):

- Unas order-create API integration with channel/store flag; per-variant SKU mapping quote→order lines (no generic SKUs).

- SKU promotion service: deterministic SKU scheme per variant (base lens × coating × diameter × Rx-range cell as applicable), product-create call to Unas, promotion registry szempont.sku_promotions; existing Unas→Tharanis product sync carries the SKU onward.

- Munkalap PDF template (branded); order registry szempont.orders mirroring Unas IDs for joins.

- Failure handling: retry queue, manual reconciliation view.

Interfaces:

- Writes: Unas API (product create for promotion; order create). Reads: Unas order status (existing pull). Downstream: existing Unas→Tharanis posting untouched.

Dependencies: M1, M2, M3. Unas API write access confirmed for shop 43321 store channel.

Acceptance: 10 pilot orders flow floor → Unas → Tharanis with correct lines, prices, VAT and customer, incl. at least 3 first-sale SKU promotions; munkalap accepted by Műhely staff as complete.

### M5 — Shell, Auth & Deployment

Priority: P0

Estimate: 1–2 engineer-days · 0.5 Sabie-days

Purpose: Production-grade wrapper: authentication, roles, navigation, deployment.

Functionality (user-facing):

- Google IAP login; roles: sales, store-manager, admin (discount limits, override rights, catalog admin).

- Atlas nav integration; audit log of sensitive actions (discounts, cancellations).

Build tasks (technical):

- Cloud Run service + IAP per Atlas pattern; nav.json entry on assets.atlas.eoptika.hu; role claims middleware; structured audit log to BigQuery.

Interfaces:

- IAP / Identity Platform (existing patterns).

Dependencies: Atlas dev kit (existing).

Acceptance: Role restrictions enforced in UAT; audit entries visible for a discount and a cancellation.

## 3.1 MIN totals & wave plan

| Wave | Content | Eng-days | Sabie-days |
| --- | --- | --- | --- |
| W1 | M1 ingest via FS6 Converter + M2 pricing engine (headless, test-first) | 5–7 | 1 |
| W2 | M2 UI + M3 customer layer | 4–5 | 1.5 |
| W3 | M4 order path + SKU promotion + munkalap + M5 shell | 5–7 | 2 |
| UAT | Floor pilot, 10 live orders, fixes | — | 1–2 |

Review gates: end of each wave (adversarial cross-session review pattern). Go-live criterion: one full week of floor orders captured in Szempont with zero manual ERP corrections.

# 4. MAX Build — Full ClearVis Replacement (M1–M12)

MAX = MIN + seven modules. Four are thin integration contracts (M6–M9), three are substantive (M1x catalogs, M10 inventory, M11 migration), plus M12 multi-store/reporting. Each is independently green-lightable after MIN validates on the floor.

### M1x — Extended Catalog Coverage

Priority: P2

Estimate: 4–6 engineer-days · 2 (per-supplier validation) Sabie-days

Purpose: Grow M1 from 1–2 suppliers to full coverage (5–8 suppliers), including proprietary Excel/CSV formats where SF6 is not distributed.

Functionality (user-facing):

- All active lens suppliers searchable in one picker; per-supplier availability and lead-time flags; house price list layer (category-based retail pricing across suppliers).

Build tasks (technical):

- Per-supplier adapter modules to the common szempont.lens_catalog_* schema; house price list table + category mapping; catalog diff/QA tooling extended.

Interfaces:

- Same outputs as M1.

Dependencies: M1 live; sample files per supplier.

Acceptance: Every supplier used in the last 12 months of spectacle orders is quotable in the picker.

### M6 — IRIS Rx Connect

Priority: P1

Estimate: 2–3 engineer-days · 0.5 (contract sign-off) Sabie-days

Purpose: Read and write prescriptions through the IRIS Rx module (built in IRIS, not here). Szempont is a client only.

Functionality (user-facing):

- Rx history panel on the customer card; select an Rx into a quote/order; enter a new external Rx (paper prescription) which is stored in IRIS, not locally.

- Rx-renewal-relevant fields exposed to retention programmes automatically (via IRIS).

Build tasks (technical):

- Define Rx read/write contract now (half-day with IRIS spec); build against a stub; swap to live endpoint when IRIS ships the module.

- Validation rules on Rx entry (sphere/cyl/axis/add ranges) shared as a library with IRIS.

Interfaces:

- IRIS Rx API (contract-first, stubbed). IRIS lives on the same GCP/BigQuery instance, so customer profiles and Rx specs are directly accessible to Szempont via read contract — the health-data boundary is architectural (IRIS owns writes/retention), not physical.

Dependencies: Contract definition only; IRIS module ships independently.

Acceptance: Order created from a stubbed Rx; on IRIS go-live, the same order path works against real data with zero Szempont changes.

### M7 — Műhely Interface (glazing handoff + status)

Priority: P1

Estimate: 3–4 engineer-days · 1 (interface contract w/ lab reality check) Sabie-days

Purpose: Hand off spectacle jobs to the future Műhely software and receive status feedback. The glazing logic tree lives in Műhely software, not here.

Functionality (user-facing):

- Spectacle order automatically creates a Műhely job (payload: munkalap data, frame source, lens ETA); job status (received / lenses ordered / glazing / QC / ready) visible on the order and to customer-facing staff.

- Ready-for-pickup event triggers a customer notification via M9.

Build tasks (technical):

- Define job + status-event contract (JSON schema, Pub/Sub or webhook); build stub "Műhely lite" queue view so MAX is usable before Műhely software exists (minimal list + manual status buttons — deliberately not a workflow engine).

- Status writeback to szempont.orders and to WIMO Stage 4a feed (shared contract — coordinate with WIMO spec).

Interfaces:

- Pub/Sub topics szempont.muhely.jobs / .status (stub consumer included). Shared with WIMO 4a.

Dependencies: Contract coordination with WIMO spec (existing) and future Műhely project.

Acceptance: Job payload accepted by stub; status round-trip updates order and fires notification event.

### M8 — Szamlazz.hu Invoicing

Priority: P1

Estimate: 2–3 engineer-days · 0.5 Sabie-days

Purpose: NAV-compliant invoice issuance as a simple API call at point of sale or pickup.

Functionality (user-facing):

- One-click invoice (and sztornó/credit note) from the order; deposit → final invoice handling; invoice PDF printed/emailed; invoice number stored on the order.

Build tasks (technical):

- Szamlazz.hu Agent API integration (XML), config per legal entity; mapping order lines → invoice lines incl. VAT keys; error/retry handling; invoice registry szempont.invoices.

Interfaces:

- Szamlazz.hu Agent API (account already in use via Unas — reuse credentials/entity setup).

Dependencies: None — nyugta exemption confirmed (v2).

Acceptance: 10 test invoices incl. one deposit-final chain and one sztornó reconcile in Szamlazz.hu and Quick.

### M9 — Notifications via GC Communications Module

Priority: P1

Estimate: 1–2 engineer-days · 0.5 Sabie-days

Purpose: All customer messaging (order confirmation, ready-for-pickup, delay) routed through the GC eOptika communications module — no local sending.

Functionality (user-facing):

- Event-driven messages with store-specific templates; channel selection (email/SMS) and consent handled by the comms module, not Szempont.

Build tasks (technical):

- Emit standard events (order.created, order.ready, order.delayed) with person_id + payload to the comms module intake; template keys agreed; no SMTP/SMS credentials in this codebase.

Interfaces:

- GC communications module intake contract (aligns with IRIS Beacon purpose classes).

Dependencies: Comms module intake available (or stubbed to log-only).

Acceptance: Ready-for-pickup event produces a real customer message end-to-end in pilot.

### M10 — In-store Inventory

Priority: P2

Estimate: 5–7 engineer-days · 2 (process definition + stocktake pilot) Sabie-days

Purpose: Barcode-driven stock control for the physical store: receiving, stocktake, transfers, sale decrement.

Functionality (user-facing):

- Receive goods against supplier delivery (scan-in); stocktake mode (scan-count, variance report — target: full store count within an hour, barcode-only); transfers store ↔ webshop warehouse; stock level shown on product cards in M2.

- Shrinkage/variance reporting to BigQuery.

Build tasks (technical):

- Stock master (decided v2): Tharanis is the source of truth for in-store stock; Szempont posts movements via the Tharanis SOAP connector, never owns the master. Remaining verification: Tharanis SOAP write coverage for stock movements (moved here from the order path, which stays Unas-only).

- Movement journal szempont.stock_movements; barcode scanning via keyboard-wedge scanners (no native app in this build); reconciliation views.

Interfaces:

- Writes stock movements to Tharanis (SOAP); reads current stock for display.

Dependencies: Tharanis SOAP write verification for stock movements.

Acceptance: One full pilot stocktake with variance report accepted by store manager; sale decrements master stock correctly for 1 week.

### M11 — ClearVis Data Migration

Priority: P2

Estimate: 3–5 engineer-days · 2 (mapping decisions + validation) Sabie-days

Purpose: Extract history from ClearVis and land it where it belongs: identities/purchases into IRIS ingest, documents into archive, reference data into BigQuery.

Functionality (user-facing):

- Customer + purchase history matched into the IRIS spine (raising in-store persons to A-grade); historical worksheets/Rx exported as documents pending IRIS Rx module; searchable archive of legacy records during transition.

Build tasks (technical):

- Assess ClearVis export options early (API v2 exists — apiV2 endpoints; else DB export request to vendor) (OQ-5); mapping + dedupe via IRIS tombstone-merge architecture; migration QA report.

Interfaces:

- ClearVis apiV2 / export files → GCS → BigQuery staging → IRIS ingest.

Dependencies: ClearVis apiV2 export access (verify at kickoff — no action needed from Sabie); IRIS ingest capacity.

Acceptance: Random sample of 50 ClearVis customers correctly resolved in IRIS with purchase history attached; zero duplicate persons created.

### M12 — Multi-store Readiness + Reporting

Priority: P2

Estimate: 2–3 engineer-days · 1 Sabie-days

Purpose: Parameterise everything single-store MIN hard-codes, and give management its numbers.

Functionality (user-facing):

- Store dimension on orders/quotes/stock/users; per-store daily sales dashboard (orders, revenue, conversion from quote, margin mix, attachment rates) in the Atlas data hub pattern; feeds EBITDA/ABC pipeline with store-channel granularity.

Build tasks (technical):

- store_id threading through schema + auth roles; scheduled BigQuery views labelled tool=szempont; Looker Studio or Atlas hub page.

Interfaces:

- Feeds eoptika_ebitda_outputs pipeline (store channel).

Dependencies: MIN live.

Acceptance: Dashboard matches manual till-count reconciliation for a pilot week.

## 4.1 MAX totals & sequencing

| Module | Name | Priority | Eng-days | Sabie-days |
| --- | --- | --- | --- | --- |
| M1–M5 | MIN scope | P0 | 14–18 | 5–7 |
| M8 | Szamlazz.hu invoicing | P1 | 2–3 | 0.5+ |
| M9 | GC comms notifications | P1 | 1–2 | 0.5 |
| M6 | IRIS Rx connect | P1 | 2–3 | 0.5 |
| M7 | Műhely interface | P1 | 3–4 | 1 |
| M10 | In-store inventory | P2 | 5–7 | 2 |
| M11 | ClearVis migration | P2 | 3–5 | 2 |
| M1x | Extended catalogs | P2 | 4–6 | 2 |
| M12 | Multi-store + reporting | P2 | 2–3 | 1 |
| Total | MAX |  | 36–51 | 14–16.5 |

Recommended order: MIN → M8+M9 (makes the floor self-sufficient for real sales) → M6+M7 (contracts, cheap, unblock siblings) → M11 (migration enables ClearVis switch-off) → M10 → M1x → M12. ClearVis subscription can be cancelled after M11 validation + 2–4 week parallel-run.

# 5. High-priority Options View

If review throughput is the constraint (it is), these are the three sensible stopping points:

- Option A — MIN only (P0): floor quoting + orders live; ClearVis retained for invoicing/inventory. 14–18 eng-days, 5–7 Sabie-days, 3–4 weeks. Delivers ~60% of daily-use value.

- Option B — MIN + P1 (M6–M9): floor fully self-sufficient for sales incl. invoices and customer messaging; Műhely and Rx wired by contract. ~22–30 eng-days, ~8–10 Sabie-days, ~5–6 weeks. Recommended target — the natural "replace ClearVis at the till" point.

- Option C — Full MAX: adds inventory, migration, full catalogs, multi-store. 36–51 eng-days, 14–16.5 Sabie-days, 6–9 weeks incl. parallel-run. Required before ClearVis cancellation.

# 6. Data Model & Interface Contracts (summary)

BigQuery dataset szempont (EU):

- lens_catalog_head / _types / _geometries / _prices / _coatings / _colors / _surcharges (versioned)

- lens_price_overrides (effective-dated combo prices)

- quotes, orders (mirror of Unas IDs), invoices, stock_movements, audit_log

External contracts:

- Unas API: product read (existing), order create (new, store channel), stock (M10, if Unas chosen as master)

- IRIS: A-grade person read, Z1 fallback (existing); Rx read/write (M6, contract-first stub)

- Műhely: jobs + status events via Pub/Sub (M7, shared with WIMO Stage 4a)

- Szamlazz.hu Agent API: invoice / sztornó (M8)

- GC communications module: event intake order.created / order.ready / order.delayed (M9)

# 7. Decisions Log & Remaining Items (v2)

All v1 open questions were answered on 12 July 2026. Recorded decisions:

| ID | Decision / status | Effect |
| --- | --- | --- |
| OQ-1 | All branded manufacturers (Zeiss, Hoya, Essilor, Noptiker) publish FS6; Noptiker also has other formats; Luxottica original lenses (not currently sold) would be custom-format; private label publishable as FS6. Existing FS6 Converter (GitHub) reused as parser. | M1 shrinks to 2–3 eng-days |
| OQ-1b | Catalog split: full ~500K-SKU lens catalog stays in BigQuery under Szempont management; only sold SKUs are pushed to ERP/Unas (mirrors ClearVis setup). | New M4 SKU-promotion service |
| OQ-2 | Confirmed: invoice-per-sale via Szamlazz.hu satisfies nyugta/pénztárgép rules for Teréz50 cash sales. | M8 fully de-risked |
| OQ-3 | No generic/custom SKUs from now on — every lens variation carries its own SKU. | M4 per-variant mapping + promotion |
| OQ-4 | Stock master: Tharanis, definitively. | M10 posts via Tharanis SOAP |
| OQ-6 | Host: szempont.eoptika.hu. | M5 DNS/IAP setup |
| R-2 | Rx boundary retained (IRIS owns health data) but directly readable — same GCP/BigQuery instance; customer profiles and specs consumable by Szempont via read contract. | M6 contract scope |

Remaining verifications (no Sabie action required): ClearVis apiV2 export coverage (M11 kickoff); Unas API order-create limits for the store channel (W3 sandbox order, deferred per instruction); Tharanis SOAP write coverage for stock movements (M10 kickoff). Standing mitigation: quote-builder-first rollout + 1-page cheat sheets for staff adoption.